## Regression Checklist
RC ID | Category | What to Check | Why (Risk from MERN's Changes) | Pages to Check | Result (Pass/Fail) | Notes
RC-01 | Footer Rendering | Footer (logo, Explore, Legal, Contact, social icons) appears correctly on EVERY page, not just Home | Footer is injected by JavaScript (injectFooter() in js/components.js) — if the new 'defer' attribute on scripts changed load order, footer could load late, load broken, or not load at all on some pages | All pages (Home, About, App, Founder, Leadership, Blog posts, FAQ, Careers, Contact) | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-02 | Images | No broken image icons anywhere on the site; all images display at correct size with no distortion | Images were converted to WebP and resized — check nothing was missed or corrupted in the conversion, on pages beyond the homepage | All pages, especially Blog posts and Founder page | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-03 | Interactive JS | FAQ accordion still expands/collapses correctly; mobile nav menu (hamburger, if any) still opens/closes | Scripts were marked 'defer' to reduce blocking — this changes execution timing and can silently break JS that expected to run immediately | FAQ page, Homepage FAQ section, any page with a mobile menu | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-04 | Horizontal Overflow | No page has unwanted horizontal scrolling or clipped content on desktop or mobile | A global 'overflow-x:hidden' rule was added — this can hide/clip legitimate wide content (e.g. code blocks, wide tables, wide images in blog posts) instead of just fixing the stats-card bug | Blog posts, About page, any page with tables/wide content | Fail | On Galaxy Z Fold, homepage stats row still overflows — 3rd card ("Currencies Supported") is cut off at the right edge. Same root cause as ISS-02's partial fix. All other checked pages/devices are clear.
RC-05 | Tablet Layout (other pages) | Pages other than Home/Careers also render correctly at 768px and 1024px widths (no overlap, no cut-off content) | New tablet breakpoints (768px, 1024px) were added site-wide — could affect pages that were previously fine at these widths | About, App, Founder, Blog, FAQ, Contact | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-06 | About Page Redesign | About page overall layout still looks correct around the new analytics mockup image (spacing, surrounding text, no overlap) | The analytics mockup was replaced with a static image — check the new image doesn't break surrounding layout or load slowly | about-app.html | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-07 | Previously-Passing: Cross-Browser | Homepage and 2-3 other key pages still render identically in Chrome, Firefox, and Edge | Re-confirm this still holds after all the CSS/JS changes (was Pass before fixes) | Home, About, Careers | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-08 | Previously-Passing: Font/Color Consistency | Fonts and colors are still consistent across all pages | Re-confirm — extensive CSS changes were made for the responsive fixes | All pages (spot-check 5-6) | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-09 | Previously-Passing: Blog Links | All blog 'Read Article' links still open the correct, complete articles | Re-confirm blog pages weren't affected by image/script changes | Blog listing + 3 articles | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-10 | Previously-Passing: Footer Legal Links | Privacy, Terms, Contact, Disclaimer, Support links in footer still all work | Re-confirm footer links weren't broken while fixing ISS-16/20/21 | Footer on any page | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-11 | Previously-Passing: Social Icons Destination | Facebook, Instagram, LinkedIn, YouTube, TikTok icons still link to the CORRECT profiles (even though ISS-21 tab-target is still open) | Confirm the target="_blank" fix attempt (if any) didn't accidentally change the href/destination | Footer on any page | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-12 | Previously-Passing: Mobile 375px Stacking | Sections still stack correctly and CTAs remain tappable at 375px width (small phone) | Re-confirm after overflow-x and stats-grid CSS changes | Home, About, Careers | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-13 | Console Errors | No new JavaScript errors appear in the browser console on page load | Deferred scripts + injected footer/nav are a common source of silent JS errors | Home, About, Careers, Founder (open DevTools > Console on each) | Pass | Confirmed clear on this regression pass (20 Aug 2026).
RC-14 | Page Load Performance (sanity check) | Pages still load in a reasonable time, no visible flash of missing footer/nav before it injects | General sanity check after defer changes | Home, About | Pass | Confirmed clear on this regression pass (20 Aug 2026).