## Fix Verification
ISS ID | Area | Original Issue | Severity | MERN Status | Verification Result | Verification Notes
ISS-01 | Broken Link | GitHub link in Mian Usman Khalid's founder profile section returns a 404 Not Found error. | High | Claimed Fixed | Still Broken | CONFIRMED LIVE (20 Aug 2026): GitHub link on the live founder profile page still redirects to the repository URL and shows a 404 error. Link text/wording may have changed but the destination is still broken.
ISS-02 | Responsiveness | Homepage content shows uneven spacing on one side on mobile view; layout not properly centered. | Medium | Claimed Fixed | Partially Fixed | CONFIRMED LIVE (20 Aug 2026): Overall page centering/alignment is fixed. However, the stat-cards row (now 5 cards) still overflows on mobile — the 5th card is cut off at the screen edge, same class of bug as before, just shifted to a different card after content was added.
ISS-03 | Broken Link | "Mock Interview" booking link uses an external Google Form instead of a hisabdo.app page. | Low | Not addressed | Not Fixed | Mock Interview button still links to an external Google Form (forms.gle/Ff8XcsXEbMWjxEvV7), same as before. Low severity, informational only.
ISS-04 | Form Validation | Careers/Internship form accepts invalid email formats without showing a validation error. | High | Out of Scope | Out of Scope (External Form) | Careers/Internship "Apply Now" button links to an external Google Form (forms.gle/YhAfaw1CzCF9mEZo9) — this is NOT part of the MERN codebase. Email/phone/file-type/city validation cannot be fixed here; must be fixed in Google Forms settings by whoever owns that form.
ISS-05 | Form Validation | Phone number field accepts alphanumeric characters and values shorter than required digit count. | Medium | Out of Scope | Out of Scope (External Form) | Same external Google Form as ISS-04 — phone validation is outside this codebase.
ISS-06 | Form Validation | CV/Resume upload accepts disallowed file types instead of rejecting non-PDF/DOC files. | High | Out of Scope | Out of Scope (External Form) | Same external Google Form as ISS-04 — file-type validation is outside this codebase.
ISS-07 | Form Validation | City field accepts random/non-existent values without validation. | Low | Out of Scope | Out of Scope (External Form) | Same external Google Form as ISS-04 — city validation is outside this codebase.
ISS-08 | UI/UX | Android-only availability disclosed only in FAQ, not near the homepage Download CTA. | High | Not addressed | Not Fixed | No "Android only" text/badge found near the Download CTA on index.html — only a Google Play icon, which is not an explicit platform disclosure.
ISS-09 | UI/UX | Homepage is long with repetitive/overlapping sections, causing scroll fatigue. | Medium | Not addressed | Not Fixed | Homepage section structure (Roadmap/Benefits/Who Should Use/etc.) appears unchanged — not consolidated.
ISS-10 | UI/UX | No real user testimonials or ratings shown — only feature claims. | Medium | Not addressed | Partially Fixed | A new section with class "review-card" was added, but its content is generic "Use Case" copy (Daily khata tracking, Freelance expense tracking, etc.) — not real user testimonials, names, or ratings. Cosmetically named like reviews but doesn't fulfil the original ask.
ISS-11 | UI/UX | Several near-duplicate CTAs across the page dilute user focus. | Medium | Not addressed | Not Fixed | CTA wording still varies: "Download Free", "Download Now — Free", and "Explore Features" all still present across pages.
ISS-12 | Responsiveness | Cookie-consent "Accept" button clipped at the right edge on multiple screen sizes. | High | Claimed Fixed | Unable to Verify | Banner did not appear during this test — likely because the browser already has hd_cookie_consent saved in localStorage from an earlier visit, so the site correctly skips showing it again. To genuinely re-test: open in an Incognito/Private window, or clear site data for hisabdo.app, then reload and check if the Accept button is fully visible.
ISS-13 | Responsiveness | iPad Mini/Galaxy Z Fold layout doesn't adapt properly (narrow column / content cut off). | Medium | Not addressed | Fixed | CONFIRMED LIVE (20 Aug 2026): iPad Mini and Galaxy Z Fold layouts now render correctly, no cropping or narrow-column issue.
ISS-14 | Responsiveness | Careers page: inconsistent section widths (info cards full-width, Open Roles narrow-centered). | Medium | Not addressed | Not Fixed | Careers page "Open Roles" section still uses max-width:760px; margin:0 auto — still narrower than the full-width info-cards section above it.
ISS-15 | Functional | Founder page "Contact" CTA button performs no action when clicked. | High | Not in MERN notes | Fixed | Founder page Contact button now uses href="mailto:support@hisabdo.app" — functional. Recommend a quick live click-test to confirm the mail client opens.
ISS-16 | Navigation | Footer "Explore" menu missing a direct "About" link. | Low | Not addressed | Not Fixed | Footer "Explore" list still has no entry literally labeled "About" — only "App" (links to about-app.html). about.html exists but isn't linked from the footer.
ISS-17 | UI/Layout | About page analytics mockup cropped/misaligned, chart axis labels irregular. | Medium | Not in MERN notes | Fixed | The old text/chart mockup was replaced with a static designed image (analytics.webp) with explicit width/height — cropping and misalignment issue no longer applies.
ISS-18 | Content | Analytics mockup amounts lack currency symbol/comma separators. | Low | Not in MERN notes | Fixed | Same fix as ISS-17 — raw-number stat cards were removed entirely along with the redesign, so the formatting issue no longer applies.
ISS-19 | UX | Founder page "Publications" section has duplicate CTAs to same destination. | Low | Not in MERN notes | Fixed | Publications section now has a single link ("View all publications →") instead of two duplicate CTAs.
ISS-20 | Navigation | Footer mailto link doesn't open the default email client. | Medium | Not in MERN notes | Fixed | CONFIRMED LIVE (20 Aug 2026): footer mailto link opens the email client correctly.
ISS-21 | Navigation | Social media icons open in the same tab instead of a new tab. | Low | Not addressed | Not Fixed | Social media icons in the footer (Facebook, Instagram, LinkedIn, YouTube, TikTok) still have no target="_blank" — will still open in the same tab.